## Phase II
{LOGO}
Project Estimate Phase II -- Main App Development
| {CLIENT_NAME} Mobile Web App |  |  | Person Weeks | 32.725 | Updated {TODAY_DATE}
|  |  |  | Total Hours | 1309
milestone | item description | assigned | month | est. hours | rate | est total | notes
1 | DNS | jm | oct | 1 | 20 | 20 | setup dns for api server(s)
1 | SSL | jm | oct | 4 | 90 | 360 | get ssl cert (256 bit)
1 | End-user requirements, research, project scope Changes | jm | oct | 20 | 120 | 2400 | any additional time set aside for refining project scope and project details
1 | Production API/Database Server setup | jm | oct | 16 | 120 | 1920 | staging and production server setup
1 | Jenkins¦Slack¦AWS monitoring, scheduled tasks, and Automated Error handling | jm | oct | 8 | 120 | 960 | setup security and availability based server scheduled tasks, log rotation, cleanup, service monitoring
1 | Setup Android dev test environment | jm | oct | 16 | 120 | 1920 | React-Native Android app dev for client, IntelliJ (Android Studio) for custom functionality, Nexus 5 (targeting v. JellyBean 4.1.1) emulator. Test in Nexus 7 running Lollipop
1 | Setup iOS dev test environment | jm | oct | 16 | 120 | 1920 | React-Native iOS app dev for client, Xcode for custom functionality, iPhone 4" screens and retina iPad, emulator. Test on iOS 9
1 | Setup email templates, notification and backend files | jm | oct | 8 | 120 | 960 | Testing and validation of email notifications, scheduled system broadcasts.
1 | Creating and loading test data, sample courses, importing static existing data (from GHN etc.) | jm | oct | 16 | 120 | 1920 | Create stubs for Phase III realtime integrations ready to be implemented
1 | REST api test and validation setup | jm | oct | 16 | 120 | 1920 | Automate testing of the REST api setup service monitoring
1 | Design and UX Analysis and Review, Design and Implement Enhancements (Andres Acosta) | ar, jm | oct | 24 | 160 | 3840 | Thorough overview and refinement of entire front end design, review requirements, transitions, LNF, colors, layout, screens, image assets
1 | Design and UX InvisionApp mockup user review | ar, jm | oct | 24 | 160 | 3840 | Material Design / React Native and React.js with MDL for web views
2 | Secure expert messaging module | jm | oct/nov | 40 | 120 | 4800 | Backend support for secure messaging with experts
2 | Rapid Assessment taxonomy: creating an Object and Code heirarchy to support data collection forms based upon variable damage parameters. Any number of inputs and data types supported, photos, drawings, notes, dimensions, checkboxes, dropdowns, date pickers etc. | jm | oct/nov | 40 | 120 | 4800 | Backend support for hierarchy and categorization of Rapid Assessment and Response documents (taxonomy for N-variable assessment data capture including data entry forms)
2 | Courseware Module, database, Object and Code heriarchy to support course display, text, authorship, images, videos, hyperlinks and app launchers. | jm | nov | 40 | 120 | 4800 | Backend support for courseware taxonomy and management
2 | System administration Dashboard (WEB screens required) | ar,jm | nov | 40 | 120 | 4800 | Not included in the mockup, this set of screens is for internal use by system administrators for managing users, content, and security functionality
2 | Document parsing module: ability to parse doc files into ready-made courses (Courseware module) | jm | nov | 80 | 120 | 9600 | Critical to the courseware as well as asset upload, this module accepts Powerpoint and Word Document uploads. Standardizes the content format (mostly stripping it) and breaks the files down into system courses with text and images, ready for final edits.
2 | Secure upload module | jm | nov | 60 | 120 | 7200 | Backend support for secure uploads
2 | Offline device data encryption | jm | nov | 60 | 120 | 7200 | Ability to securely encrypt offline content in case of compromised device
2 | Emergency wipe (delete all info, overwrite device flash, obfuscate app) | jm | nov | 40 | 120 | 4800 | Optional, possibly Phase III
2 | Course editing, image and video attachments | jm | nov | 40 | 120 | 4800 | Stripped down, standardized HTML content will make for a usable, mobile experience from a variety of content uploads.
3 | Native/Web hybrid Mobile Front-end For Android Using React-Native, Xcode, Android Studio and Eclipse (for web based React.js / JSP (see user interface screen development table) | ar,jm,pm | nov/dec | 360 | 120 | 43200 | front-end development per the InvisionApp mockup screens, based upon the breakdown in the UX table below
4 | Port Client Android App to iOS | ar,jm | dec/jan | 72 | 120 | 8640 | Port Android App to iOS assuming 80% re-use. Front-end development per the InvisionApp mockup screens, based upon the breakdown in the UX table below.
4 | Port Client Android App to Web (Admin/Content Creator functionality ONLY) | ar,jm | dec/jan | 54 | 120 | 6480 | Port Android App to web assuming 85% re-use. Intended for Admins and Content Creators to upload and edit content, so for now we leave out field Responder functions and corresponding screens not included in webapp.
4 | Notification System (Emails, Push, SMS Templates, Automation) | jm | dec/jan | 16 | 120 | 1920 | includes registering ssl certs with AWS Simple Notification Services iOS push, Android Push, SMS, integration of PUSH and email notifications with AMAL app
4 | Localization (Arabic, French) | ar, jm | dec/jan | 50 | 120 | 6000 | Right to left languages may incur additional changes to UX, Translation Services, Help System
5 | BETA Usability Analysis and Review (PM) | jm, pm | jan/feb | 20 | 140 | 2800 | Review App and beta user comments and behavior to identify and correct any inconsistencies, usability issues, navigation glitches or non-obvious enhancemants
5 | User testing and QA (ALPHA) | jm, pm | jan/feb | 40 | 120 | 4800 | Work with staff to test app with a limited set of beta users before pilot testing, fix bugs, implement minor enhancements
5 | Pilot Testing Phase (BETA) | jm | jan/feb | 40 | 120 | 4800 | Work with staff to support a limited rollout to trusted Beta users before general release
5 | Train staff on procedures, security, automated support apps and notifications | jm | feb | 12 | 120 | 1440 | we have automated support customer service systems, issue trackers, etc.
5 | Setup deployment services (App Store, Play Store, ad hoc, etc.) | jm | feb | 12 | 120 | 1440 | dependent upon deployment scenarios.
5 | Training & documentation | jm | feb | 24 | 120 | 2880 | dedicated time for supporting new users, email and phone training
5 | Final acceptance testing | ar,jm,pm | feb | 0 | 120 | 0 | final cleanup and bugfixing, free of charge for 30 days
5 | Project Management ¦ Communication ¦ Administration |  |  | 104.72 | 120 | 12566.4
[5 empty] | total | 171746.4
[5 empty] | nonprofit customer discount | 51523.92 | 30%
[5 empty] | estimate total | 120222.48
[5 empty] | downpayment | 24044.496
| ux screen development estimate |  |  | est hours
| Locations Details |  |  | 16
| Locations List |  |  | 8
| Assessment Form |  |  | 20
| Assessment List Item Form |  |  | 10
| Locations Map |  |  | 10
| Locations Assets |  |  | 12
| Dashboard Expert |  |  | 24
| Dashboard |  |  | 16
| Profile Intro |  |  | 12
| Profile Gallery |  |  | 12
| Profile Assets |  |  | 12
| Profile Course List |  |  | 16
| Settings x 3 |  |  | 16
| Courses Upload |  |  | 24
| Courses List |  |  | 16
| Course Detail |  |  | 20
| Courses Edit |  |  | 20
| Courses Image |  |  | 16
| Courses GotoMeeting Signup |  |  | 8
| Courses Section View |  |  | 12
| Courses Taxonomy/Heirarchy |  |  | 16
| Messages List |  |  | 20
| Messages Detail / Reply / Edit |  |  | 24
|  | total |  | 360
|  | average hrs/screen |  | 15.6522
| estimated 1st year server/capital costs |  |  | months | per month | annual | description
| AWS services (ec2, s3, elb, sns, etc.) |  |  | 12 | 350 | 4200 | Main cloud hosting for app and server (assuming 2 EC2 instances, 1 RDS instance + S3 storage of 100 GB data)
| Basecamp, Slack, Bitbucket, Terminal.com (Jenkins, Huginn, Test) instances and other services |  |  | 12 | 50 | 600 | Additional support services
| Staging server (AWS) |  |  | 6 | 50 | 300 | EC2 instance for staging new versions & live testing (not always running)
| Hot backup instances (chunkhost, terminal.com) |  |  | 12 | 40 | 480 | Live non-AWS cloud “insurance policy” instances ready to use in case of unlikely AWS failure
|  |  |  | total | 490 | 5580
| estimated Year 2+ Maintenance Options |  |  |  | per month | annual | description
| 12 months best effort email support |  |  | 1 | 1431.22 | 17174.64 | Annual Support + Maintenance
| 12 months premium email and phone support ***** |  |  | 1 | 3220.245 | 38642.94 | Annual Support + Maintenance
| 12 months enhanced email and phone support ****** |  |  | 1 | 3578.05 | 42936.6 | Annual Support + Maintenance
* | On-site work charged @ $350 per diem + expenses.
** | This is only an estimate. No guarantee of final cost is made.
*** | In the event of a line-item going over 10% of estimated time, we will notify before undertaking work and discuss a change authorization before proceeding.
**** | All software source code provided. Perpetual Apache v2.0 License or GPLv3 redistributable copyleft licensing.
***** | Includes operating system and library upgrades and patching, system monitoring with 8 hour response, support inbox monitoring, and hot fixes to product software up to 15 hrs. Month.
****** | Includes operating system and library upgrades and patching, system monitoring, and hot backup maintenance, with 6 hour response, support inbox monitoring, and hot fixes and enhancements to product software up to 30 hrs. Month.

## Phase III
Project Estimate Phase III -- Enhancements Development
| Global Heritage Fund Mobile and Web App | Person Weeks | 13.9
|  | Total Hours | 556
| item description | est. hours | rate | item total | notes
| Usashi Crowdmap API Integration | 120 | 120 | 14400 | display and embed crowd map posts using Usashi REST api — ability to display heritage assets and sites on crowdmap, links from AMAL to crowdmap items,
| GotoMeeting/Google Hangout API Integration | 40 | 120 | 4800 | schedule, launch, and link to GotoMeeting sessions from within AMAL courses, integrate with course schedule, integrate with post-meeting quizzes
3 | Quiz module | 40 | 120 | 4800 | Backend support for quizzes including database schema, tabulation and scoring
3 | Integrate Drawing Module | 40 | 120 | 4800 | Backend and client support for sketching capability. Potential integration with Sketch app
| App screen development | 56 | 120 | 6720 | see User Interface Screen Development Estimate breakout table
| Additional parsed uploaded file types (PDF, Excel, …?) | ? | 120 |  | depends greatly upon file format
| Extra-Secure data upload “muxing” (+ Extra Server Costs) | 60 | 120 | 7200 | possibly overkill
| Offline data synchronization | 40 | 120 | 4800 | Ability to store large uploads for future upload when offline
| Heritage Site First Aid Checklist module | 40 | 120 | 4800 | this will be integral to the user experience, and a critical part of ensuring accurate, - push/email confirmation of checklist (do you have video, images, proper notations, etc.)
| Advanced Photographic “Walkthrough”, photo enhancement module for site assessment assistance | 60 | 120 | 7200 | much like the panoramic shot assistants, we would enable a methodological interactive camera guides for capturing data onsite
| Facebook ¦ Twitter ¦ XYZ Social network Integration | 40 | 120 | 4800 | roughly per integration
| “Calculator” Lock Screen | 20 | 120 | 2400
| Implementing 3D Scanner Uploads (Depends upon Hardware) | ? | 120
|  | 0 | 120 | 0 | final cleanup and bugfixing, free of charge for 30 days
| Project Management ¦ Communication ¦ Administration | 55.6 | 120 | 6672
|  |  | . | 73392
|  |  | Nonprofit Customer Discount | 5760 | 30%
|  |  | Estimate Total | 67632
|  |  | Down payment | 13526.4
| User Interface Screen Development Estimate | est. hours
| Courses GotoMeeting Signup | 8
| Quiz View | 24
| Quiz Edit | 24
| total | 56